## Sheet1
Task ID | Phase | Task Description | Start Date | End Date | Status | Completed (%) | Notes
1 | Setup | Work on Iteration2 overleaf | 2025-10-24 | 2025-10-26 | Completed | 100%
2 | Setup | Create Github Repo and folder structure | 2025-10-26 | 2025-10-26 | Completed | 100%
3 | Setup | Set up environment | 2025-10-24 | 2025-10-27 | In-Progress | 70% | Still double checking what other libraries and file-setup
4 | Data Preparation | Download MovieLens Dataset | 2025-10-25 | 2025-10-25 | Completed | 100% | Exploring
5 | Data Preparation | Clean and preprocess dataset | 2025-10-25 | 2025-10-27 | In-Progress | 50% | Handling nulls, normalizing ratings
6 | Modeling | Implement collaborative filtering model | 2025-10-26 | 2025-10-29 | Not Started | 0% | Using 'Surprise' Library
7 | Modeling | Implement Content-Based filtering model | 2025-10-30 | 2025-11-02 | Not Started | 0%
8 | Modeling | Hybrid recommendation approach | 2025-11-03 | 2025-11-09 | Not Started | 0%
9 | Reporting | Generate SQL analytical reports | 2025-11-05 | 2025-11-09 | Not Started | 0% | movie popularity and trends
10 | Front-end | Build Flask/HTML interface | 2025-11-10 | 2025-11-15 | Not Started | 0% | MVP user iterface
11 | Documentation | Finalize PDF report | 2025-11-15 | 2025-11-16 | Not Started | 0% | Prepare for submission
12 | Documentation | Upload file to github | 2025-11-16 | 2025-11-16 | Not Started | 0% | Final